## Sheet1
Team Backlog |  |  |  |  | Hacker Kermit
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Layered Architecture | All Team | Done | 1 | 1
Simulation (Project Circuit Schematic) | Tarek | Done | 0.5 | 0.5
Modules' Description | All Team | Done | 1 | 2
Drivers' Documentation | All Team | Done | 3 | 4
Low Level Design
Functions' Flowchart | All Team | Done | 3 | 4
Summary
Document File | Hossam | Done | 3 | 3
Implementation
MCAL Module
DIO Driver | Hossam | Done | 1 | 1
ADC Driver | Abdelrhman | Done | 3 | 2
TMR Driver (need uS timer) | Mahmoud | Done | 1 | 5
HAL Module
BUZ Driver | Tarek | Done | 1 | 1
KPD Driver | Abdelrhman | Done | 3 | 2
LCD Driver | Hossam | Done | 3 | 3
TSI Driver | Mahmoud | Done | 3 | 3
APP Module
APP Module | Mahmoud & Hossam & Abdelrahman | Done | 4 | 15
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 2 | 3
Unit Testing
Test MCAL | All Team | Done | 3 | 4
Test HAL | All Team | Done | 3 | 4
System Testing
Test APP | All Team | Done | 1 | 1
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | Mahmoud | Done | 1 | 1
Video Editing | Hossam & Abdelrhman | Done | 1 | 1