## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Layered Architecture | All Team | Done | 1 | 1
Simulation (Project Circuit Schematic) | Tarek | Done | 0.5 | 0.5
Modules' Description | All Team | Done | 1 | 2
Drivers' Documentation | All Team | Done | 3 | 4
Low Level Design
Functions' Flowchart | All Team | Done | 3 | 4
Summary
Document File | Hossam | Done | 3 | 3
Implementation
MCAL Module
DIO Driver | Hossam | Done | 1 | 1
ADC Driver | Abdelrhman | Done | 3 | 2
TMR Driver (need uS timer) | Mahmoud | Done | 1 | 5
HAL Module
BUZ Driver | Tarek | Done | 1 | 1
KPD Driver | Abdelrhman | Done | 3 | 2
LCD Driver | Hossam | Done | 3 | 3
TSI Driver | Mahmoud | Done | 3 | 3
APP Module
APP Module | Mahmoud & Hossam & Abdelrahman | Done | 4 | 15
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 2 | 3
Unit Testing
Test MCAL | All Team | Done | 3 | 4
Test HAL | All Team | Done | 3 | 4
System Testing
Test APP | All Team | Done | 1 | 1
Final Requirements Review | All Team | Done | 1 | 1
Video
Video Recording | Mahmoud | Done | 1 | 1
Video Editing | Hossam & Abdelrhman | Done | 1 | 1

## Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
MCAL Module
DIO Driver
TC_DIO_001 | Test DIO initialization | 1. Call DIO_init with valid parameters | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_002 | Test DIO read | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 3. Call DIO_read | u8_a_value is returned as 1 | Matches Expected Result | Pass
TC_DIO_003 | Test DIO write | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_004 | Test DIO toggle | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 3. Call DIO_toggle 4. Call DIO_read | u8_a_value is returned as 0 | Matches Expected Result | Pass
TC_DIO_005 | Test port initialization | 1. Call DIO_portInit with valid parameters | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_006 | Test port write | 1. Call DIO_portInit with valid parameters 2. Call DIO_portWrite with a value of 0x55 and a mask of 0xFF (DIO_NO_MASK) | The specified port pins are set to 0x55 | Matches Expected Result | Pass
TC_DIO_007 | Test port toggle | 1. Call DIO_portInit with valid parameters 2. Call DIO_portWrite with a value of 0x55 and a mask of 0xFF (DIO_NO_MASK) 3. Call DIO_portToggle with a mask of 0xFF (DIO_NO_MASK) 4. Call DIO_portWrite with a value of 0xAA and a mask of 0xFF (DIO_NO_MASK) 5. Call DIO_portToggle with a mask of 0xFF (DIO_NO_MASK) | The specified port pins are toggled between 0x55 and 0xAA | Matches Expected Result | Pass
TC_DIO_008 | Re-Test with invalid data | Re-test cases from 1 to 7 with invalid data | Return DIO_ERROR | Matches Expected Result | Pass
TIMER Driver
TC_TIMER_001 | Test timer0 & timer2 Init | 1. Call TMR_timer0NormalModeInit & TMR_timer2NormalModeInit | The two timers working in the normal mode | Matches Expected Result | Pass
TC_TIMER_002 | Test timer0 delay function | 1. Call TMR_timer2Delay with deferent delay ranges | The desired delay is acheived | Matches Expected Result | Pass
TC_TIMER_003 | Test timer2 delay function | 1. Call TMR_timer0Delay with deferent delay ranges | The desired delay is acheived | Matches Expected Result | Pass
TC_TIMER_004 | Test timer0 & timer2 start | 1. Call TMR_timer0Start & TMR_timer2Start | The two timers start working in normal mode | Matches Expected Result | Pass
ADC Driver
TC_ADC_001 | Test ADC Initialization | Call ADC_inialization after setting the desired configurations in adc_config.h file | ADC peripheral is enabled with the desired configurations | Matches Expected Result | Pass
TC_ADC_002 | Test ADC StartConversion | Call ADC_startConversion passing channelId (Correct parameters) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_ADC_003 | Test ADC StartConversion | Call ADC_startConversion passing channelId (Incorrect parameters) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_ADC_004 | Test ADC GetDigitalValue | Call ADC_getDigitalValue passing interruptionMode and pointer to the returned DigitalValue (Correct parameters) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_ADC_005 | Test ADC GetDigitalValue | Call ADC_getDigitalValue passing interruptionMode and pointer to the returned DigitalValue (Incorrect parameters) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
HAL Module
BUZ Driver
TC_BUZZER_001 | Test buzzer init | Call BUZZER_init() | The Buzzer module should be initialized | Matches Expected Result | Pass
TC_BUZZER_002 | Test buzzer on | Call BUZZER_on() | The buzzer should be turned on | Matches Expected Result | Pass
TC_BUZZER_003 | Test buzzer off | Call BUZZER_off() | The buzzer should be turned off | Matches Expected Result | Pass
LCD Driver
TC_LCD_001 | LCD Initialization | Call LCD_init() function. | The LCD module should be initialized and ready to display data. | Matches Expected Result | Pass
TC_LCD_002 | Sending Command | Call LCD_sendCommand() function with a valid command. | The command should be successfully sent to the LCD controller and executed. | Matches Expected Result | Pass
TC_LCD_003 | Sending Character | Call LCD_sendChar() function with a valid character. | The character should be displayed on the LCD screen. | Matches Expected Result | Pass
TC_LCD_004 | Sending String | Call LCD_sendString() function with a valid null-terminated string. | The string should be displayed on the LCD screen. If the character '\n' is encountered, the cursor should move to the beginning of the next line. | Matches Expected Result | Pass
TC_LCD_005 | Setting Cursor Position | Call LCD_setCursor() function with valid line and column values. | The cursor should be set to the specified line and column on the LCD screen. | Matches Expected Result | Pass
TC_LCD_006 | Storing Custom Character | Call LCD_storeCustomCharacter() function with a valid bitmap pattern and location. | The custom character should be successfully stored in the CGRAM of the LCD module. | Matches Expected Result | Pass
TC_LCD_007 | Clearing Display | Call LCD_clear() function. | The LCD screen should be cleared and the cursor should be returned to the home position (line 0, column 0). | Matches Expected Result | Pass
TEMPSENSOR Driver
TC_TS_001 | TempSensor Inintialization | call ADC_init() function | The ADC module shoud be intialized. | Matches Expected Result | Pass
TC_TS_002 | TempSensor get Value | Call the ADC_StartConversion , Call the ADC_getValue functions, and storing the temperature value | The temperature value should be stored in the passed addres | Matches Expected Result | Pass
KPD Driver | [5 empty] | KPD Driver | KPD Driver
TC_KPD_001 | KPD_initKPD | Call the KPD_initKPD | Rows Pins are set as Output, Columns Pins are set as Input (enabling pullup resistor) | Matches Expected Result | Pass
TC_KPD_002 | KPD_enableKPD | Call KPD_enableKPD | Rows Pins are set as Output (enable or re-enable KPD) | Matches Expected Result | Pass
TC_KPD_003 | KPD_disableKPD | Call KPD_disableKPD | Rows Pins are set as Input (disable KPD) | Matches Expected Result | Pass
TC_KPD_004 | KPD getPressedKey | Call KPD_getPressedKey passing pointer to the returned KeyValue (Correct parameters) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_KPD_005 | KPD getPressedKey | Call KPD_getPressedKey passing pointer to the returned KeyValue (Incorrect parameters) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
APP Module
TC_APP_001 | APP_initialization() | Call all modules' initialization functions. | All modules should be initialized. | Matches Expected Result | Pass
TC_APP_002 | APP_startProgram() | Switches on the pressed key, call the timeout function, and the temperature change function. | It switches between two states, adjust and running, and performs different tasks in each one. | Matches Expected Result | Pass
TC_APP_003 | APP_switchState() | Call the BUZZER_off(), LCD_clear, KPD_disableKPD(),LCD_setCursor,..... | Switch between AC states "running" and "adjust" | Matches Expected Result | Pass
TC_APP_004 | APP_changeTemp() | Call LCD_sendChar(), LCD_setCursor(), LCD_sendString(), TIMER_delay_ms(), BUZZER_off(). | Update UI temp value, progress bar, handling the Corner Cases,Update UI with new desired temp | Matches Expected Result | Pass
TC_APP_005 | APP_resetToDefault() | Call LCD_clear(), LCD_sendString(), TIMER_delay_ms(), APP_switchState(). | Resets the desired temperature value to the default temperature. | Matches Expected Result | Pass